## Sheet1
Bug report for Para Bank
Link : https://parabank.parasoft.com/
Bug ID | Description | Severity | Priority | Steps to Reproduce | Status
BUG-001 | Clicking on ATM Services / Bill Pay / Transfer Funds / Account History without logging in shows raw XML/WSDL backend file instead of a proper error message. | High | Medium | 1. Open https://parabank.parasoft.com 2. Do NOT login 3. Click on ATM Services / Bill Pay / Transfer Funds / Account History 4. Observe the page that appears | Not Fixed
BUG-002 | Signup form allows invalid input in fields (e.g., numbers in First Name/Last Name, letters in ZIP/Phone/SSN) without validation. | Medium | High | 1. Open signup page 2. Enter invalid data like: - First Name: 1234 - Last Name: 5678 - ZIP: aaa - Phone: aaaaaaa - SSN: aaaaaaaa 3. Click REGISTER 4. Observe that form accepts invalid data | Not Fixed
BUG-003 | Password field does not have an eye icon to toggle visibility; users cannot see the password they are typing. | Low | Medium | 1. Open login or signup page 2. Go to Password field 3. Observe that there is no eye icon to show/hide password | Not Fixed
BUG-004 | Newly created account shows 515 Indian Rupees instead of $0 (or expected currency). | Medium | High | 1. Complete signup and create a new account 2. Observe initial account balance | Not Fixed
BUG-005 | Funds Transfer allows sending any amount even when account balance is insufficient. | High | High | 1. Sign up / log in to the app 2. Go to Funds Transfer 3. Enter an amount greater than your account balance 4. Submit transfer 5. Observe that transfer is processed successfully | Not Fixed
BUG-006 | Bill Pay logs the user out when invalid account or payment data is entered instead of showing an error message: “An internal error has occurred and has been logged.” | High | High | 1. Log in to the app 2. Go to Bill Pay 3. Enter invalid account number / payment info 4. Submit payment 5. Observe that the app logs the user out instead of showing the proper error message | Not Fixed
BUG-007 | Transaction dropdown shows no data after selecting an account in Find Transactions, even if transactions exist. | Medium | High | 1. Log in to the app 2. Go to Find Transactions 3. Select an account from the dropdown 4. Observe that dropdown is empty and no transactions appear | Not Fixed
BUG-008 | Entering an invalid transaction ID in Find Transactions logs the user out instead of showing the message: “An internal error has occurred and has been logged.” | High | High | 1. Log in to the app 2. Go to Find Transactions 3. Enter an invalid transaction ID 4. Submit 5. Observe that user is logged out instead of seeing the proper error message | Not Fixed
BUG-009 | Updating contact info after login triggers: “An internal error has occurred and has been logged,” and the update fails. | High | High | 1. Log in to the app 2. Go to Upgrade Contact Info 3.Observe the error message and that contact info is not updated | Not Fixed
BUG-010 | Account balance shows INR after login, but dollars ($) are shown in Request Loan and Find Transactions sections. | Medium | High | 1. Log in to the app 2. Observe account balance (INR) 3. Go to Request Loan or Find Transactions 4. Observe amounts displayed in dollars ($) | Not Fixed
BUG-011 | After logging out, users cannot log in again with the same username/password; a new account must be created. | High | High | 1. Log in to the app 2. Log out 3. Try to log in again with the same credentials 4. Observe that login fails and a new account is required | Not Fixed